## Monday team notes
Monday staff review
Checklists deep clean
Gym cleaning
Decks how to manage with no guests in house - rugs and beds away
Compost chicken wire
Covers for AC
Water tank split hose
Jerome
7-4 hours
Bonus of $30 day is end of the month

## Maintenance
Task | Type | Priority | Owner | Location | Status | Scheduled Start | Work Days | Est Completion Date | Notes
Staff house water tank and building plan | Construction | Low | Charlotte | Grounds | In planning | 2026-06-18 | 30 | 2026-07-18 | CF scoping
Switch club house dimmer (upside down) | General | Medium | Hank | Club House | Not started |  |  |  | Club House
Gym Gutter Review, leaking on the side so not draining into the gutter | General | High | Alroy | Gym |  |  |  |  | If you look at the corner it has water dripping and standing water meaning that the water is not getting to the tank.
Replace all black switches | General | Medium | Hank | Multiple Loc | In progress |  |  |  | Check Whole Property
Landscaping to limit grass demands | General | High | Charlotte | Grounds | Completed | 2026-06-17 |  | 2026-06-17 | CF consulting landscaping consultant
Remove outdoor electrical switch |  | Low | Hank | Phillips | Completed | 2026-01-23 |  |  | By the pump there is old switch to remove ask Alroy
Delayed Lighting on Fan |  | Low | Hank | Multiple Loc | Completed | 2026-01-12 |  |  | Delayed start when turning on lights
Fix front fountain - issue persists with pump | General | Critical | Hank | Grounds | In progress | 2026-04-01 |  |  | Pump sitting out, need to try and resolve electical, cover umbrella when not in use
Hang two fans | General | Low | Hank | Multiple Loc | Completed | 2026-01-12 |  |  | Media room and Master
Doors for AC drain | General | Low | Alroy | Multiple Loc | Questions | 2026-06-21 | 1 | 2026-06-22 | Ask michael what he wants done here?
Headboards Recovered in Jasmine | General | Low | Alroy | Multiple Loc | On Hold | 2026-06-21 | 7 | 2026-06-28 | Waiting on Alecia return
Service Stoves | General | Medium | Charlotte | Club House | Completed | 2026-06-01 |  | 2026-06-01 | Reached out to chef
Pool filter | General | Critical | Michael | Grounds | Completed | 2026-06-01 |  | 2026-06-01 | Wating for quote
All remotes hung for fams | General | Medium | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01
Ghost Lighting |  | High | Hank | Hibiscus | Completed | 2026-01-12 |  |  | Did Cam replace the light?
Pool steps stonework | General | Medium | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01 | Prepping for Alroy
Hang Cameras | General | Critical | TomTom | Grounds | Completed | 2026-06-01 |  | 2026-06-01 | Check all working and set up
Tub leak | General | Medium | Alroy | Jasmine | Completed | 2026-06-01 |  | 2026-06-01 | Plumbing leaking in tub
Vinlec Pole Repair | General | High | Alroy | Grounds | Scheduled | 2026-06-19 | 120 | 2026-10-17 | Need to ask them to relocate
Install new interior doors master villas | General | Low | Alroy | Jasmine | On Hold | 2026-09-01 | 0 | 2026-09-01 | Not sure will proceed
Hang spotlights | General | Medium | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01
Slider door sticks | General | Medium | Alroy | Apple | Completed | 2026-06-01 |  | 2026-06-01 | Door keeps coming off the track
Install Doggie Door on Villa | General | Medium | Alroy | Hibiscus | Completed | 2026-06-01 |  | 2026-06-01
Hang key pad front door | General | Medium | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01
Gym Decking | General | High | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01 | Est start 1/5, finish 2 weekes
Repaint step by gym | General | Low | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01
Ice Maker Repair | General | High | Michael | Club House | Completed | 2026-06-01 |  | 2026-06-01
Bar solution - paint and OSV | General | Critical | Charlotte | Club House | Completed | 2026-06-01 |  | 2026-06-01
Order Tile Sealant | General | Critical | Charlotte | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01 | Ordered will pick up in FLA
Fix paint cracks | General | Low | Alroy | Jasmine | Completed |  |  | 0
Grout fix pool steps & sealant | General | High | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01
Family lodge leak in ceiling | General | High | Alroy | Frangipani | Completed | 2026-06-01 |  | 2026-06-01 | Just needs paint
Air in Plumbing Line Bar | General | Medium | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01
OSV AC Servicing 6 Month | General | Medium | Charlotte | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01 | CF Called OSV 1/12
Handles/doors on french patio villas | General | Low | Charlotte | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01 | Jasmine and Hisbiscus
Counter brackets | General | Medium | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01 | CF Called OSV 1/12
Shower Glass Leaks | General | High | Alroy | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01 | Jasmine & Orchid
Install accumulator tank in main lodge | General | Critical | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01
Rehang, paint bar photos | General | Medium | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01
Service all gym equipment | General | Critical | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01
De-rust game equipment | General | Medium | Alroy | Grounds | Scheduled | 2026-06-29 | 2 | 2026-07-01 | Needs a repeat
Set up lattice by garbage | General | Critical | Alroy | Grounds | Completed | 2026-02-01 |  | 46054
Ice maker repair | General | Critical | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01
Move all scones facing down |  | Low | Hank | Multiple Loc | Completed | 2026-01-12
Replace villa door handles | General | Low | Alroy | Jasmine | Completed | 2026-06-01 |  | 2026-06-01
Replace villa door handles | General | Low | Alroy | Hibiscus | Completed | 2026-06-01 |  | 2026-06-01
Roof fascia on villa | General | Medium | Alroy | Hibiscus | Completed | 2026-06-01 |  | 2026-06-01
Clear grounds pumps | General | High | TomTom | Grounds | Completed | 2026-06-01 |  | 2026-06-01
Replace villa door handles | General | Low | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01
Master Toilet Leaking | General | High | Alroy | Jasmine | Completed | 2026-06-01 |  | 2026-06-01
Shelving gym | General | Low | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01
Gym windows and doors | General | Medium | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01
Fan in media room making buzzing noise | General | Medium | Hank | Club House | Completed
Pull all ground electical | General | High | Hank | Grounds | Not started
Furniture covers outdoor | General | Critical | Charlotte | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01 | Determine what is needed
Finish furniture shuffle | General | Low | Charlotte | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01
New light above family lodge not working | General | High | Hank | Orchid | In progress
Order new entrance gates | General | Low | Charlotte | Multiple Loc | In planning | 2026-07-01 | 90 | 2026-09-29 | On hold until get other land purchase complete
Terracing down hill | Construction | Low | Glenroy | Grounds | Completed | 2026-06-18 | 0 | 2026-06-18 | Finish master, compost, pool area
Ac fix 110 to 220 in club house | General | Medium | Hank | Club House | Completed
Repair large pond | General | Low | Glenroy | Grounds | Scheduled | 2026-06-22 | 10 | 2026-07-02 | Glenroy is starting job 6/19 waiting on quote
Internet project finalize wiring | General | Low | Michael | Grounds | In planning | 2026-07-27 | 14 | 2026-08-10 | Mark coming this summer
Backup pump for club house | General | Critical | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01 | Not sure what is this?
OSV Water Heater Repairs | General | Medium | Alroy | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01 | CF Called OSV 1/12
Build cover for pumps | General | Low | Alroy | Multiple Loc | Questions | 2026-06-22 | 1 | 2026-06-23 | Cover outdoor pump, discussed PVC
Club switch timers | General | Low | Hank | Club House | In progress |  |  |  | Verify with Hank
Plumbing for ground pumps | General | High | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01 | Spouts from drains into tanks
Order water transfer pump | General | Critical | Michael | Grounds | Completed | 2026-06-01 |  | 2026-06-01 | OSV water water hoses - was this ordered
Pool step slip issue | General | Critical | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01 | Calling bunion
Robot in tanks | General | Medium | Michael | Club House | Materials Block | 2026-09-01 | 1 | 2026-09-02 | Robot does not get wifi, do we want another solution
Villa fridge cabintry | General | Medium | Alroy | Multiple Loc | Questions | 2026-06-21 | 1 | 2026-06-22
Hang smoking signs | General | Medium | Alroy | Grounds | On Hold | 2026-09-01 | 1 | 2026-09-02 | Waiting for new gates
Set wkly water limits | General | High | Alroy | Grounds | In progress | 2026-06-22 | 1 | 2026-06-23 | Grounds team currently watering 3x per wk/Jerome est 1K/wk
Security SOP | General | Low | Charlotte | Multiple Loc | In progress | 2026-07-01 | 90 | 2026-09-29 | SOP in progress, sort contractor processes, fencing
Villa switch timers | General | Low | Charlotte | Club House | Completed | 2026-06-01 |  | 2026-06-01 | CF needs to test
Solar light install & review | General | Medium | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01
Finish gym to completion | General | Medium | Alroy | Gym | In progress | 2026-05-01 | 5 | 2026-05-06 | Fill holes, caulk flooring, remove hooks outside by walls
Compost bins set up | General | Medium | Alroy | Grounds | Materials Block | 2026-06-16 | 3 | 2026-06-19 | What are the roadblocks to this?
Cold plungs hook up | General | High | Hank | Grounds | Completed |  |  |  | Sat. installation
Tile sealant inside villas | General | Medium | Alroy | Multiple Loc | In progress | 2026-06-18 | 14 | 2026-07-02 | Sealant brought 04/28; need to test grout color
Pool light (second one needs replacement) | General | Low | Hank | Grounds | In progress |  |  |  | waiting on hank
Timer for entrance pond | General | Low | Hank | Grounds | In progress |  |  |  | waiting on hank
Master Tub Handles | General | Low | Alroy | Jasmine | Not started | 2026-06-28 | 1 | 2026-06-29 | Brought replacement handles
Kitchen sink leak | General | Low | Alroy | Club House | Completed | 2026-06-01 | 1 | 2026-06-02 | Kitchen sink leak back
Villa sinks draining slowly | General | Medium | Alroy | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01 | CF brought drains and tools 04/28
Repurpose pump black tanks | General | Critical | Michael | Grounds | Completed | 2026-06-01 |  | 2026-06-01 | What do we want to do here Michael?
Cover for electical holes | General | Medium | Hank | Multiple Loc | Questions | 2026-06-23 |  | 2026-06-23 | Can he repair?
Threshold insallation | General | Low | Charlotte | Club House | Materials Block | 2026-09-01 | 1 | 2026-09-02 | Need to order new material
Finish roof metal on club house | Construction | Low | Alroy | Club House | Not started | 2026-07-01 |  | 2026-07-01
Fix top of black water tank | General | Medium | Michael | Grounds | Completed | 2026-06-01 |  | 2026-06-01 | Waiting on Michael
Roof metal on two pool villas | Construction | Low | Alroy | Grounds | Questions | 2026-07-01 | 14 | 2026-07-15 | Who can we hire? Materials status?
Shower Water Flow | General | High | Alroy | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01 | Alroy verfied on 06/17 it was complete
Replace window screens on all villas | General | High | Alroy | Multiple Loc | In progress | 2026-06-15 | 14 | 2026-06-29 | Waiting on materials
Replace ceiling screens | General | Low | Alroy | Multiple Loc | Materials Block | 2026-07-20 |  | 2026-07-20 | Order materials
Water levels recorded and managed | General | Critical | Charlotte | Multiple Loc | Questions | 2026-06-19 |  | 2026-06-19 | CF to verify levels are correct with Jerome on Friday
Remove all debris yard | General | High | Alroy | Grounds | Completed | 2026-06-01 |  | 2026-06-01
Fix master tub drain | General | Low | Alroy | Jasmine | Not started | 2026-06-22 | 1 | 2026-06-23
Replace outdoor shower head | General | Low | Alroy | Pool | Not started | 2026-06-22 | 1 | 2026-06-23 | Brought materials May
Re-caulk counter by sink in master | General | Low | Alroy | Jasmine | Not started | 2026-07-06 | 1 | 2026-07-07
Solar installation plan | Construction | Medium | Michael | Grounds | In planning | 2026-07-01 | 180 | 2026-12-28
Order concrete & block maker | General | Low | Charlotte | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01
Media Room Simply Lock | General | Medium | Charlotte | Club House | Completed | 2026-06-01 |  | 2026-06-01 | Wrong lock, new one on way
Recast the rainfall guards or remove totally | Construction | Medium | Alroy | Grounds | Questions | 2026-07-20 | 1 | 2026-07-21
OSV Hot Water Solution | General | High | Alroy | Multiple Loc | Completed | 2026-06-01 |  | 2026-06-01 | Elizabeth text
Fridge & freezer service | General | High | Alroy | Club House | Completed | 2026-06-01 |  | 2026-06-01 | Fridge and freezer technician
Landscape architect on survey lands (include parking) | Construction | Low | Charlotte | Grounds | In planning | 2026-06-19 | 10 | 2026-06-29 | Ryans scheduled next week
Setting up the newer black water tank | General | Medium | Alroy | Grounds | Questions | 2026-07-20 | 1 | 2026-07-21 | What are we doing here, club?
Pool leak | General | Medium | Alroy | Pool | Completed | 2026-06-18 |  | 2026-06-18 | Determine evaporation
Finish gym caulking floor, holes & outdoor hook removal | General | Medium | Alroy | Gym | Questions | 2026-06-18 | 1 | 2026-06-19 | CF needs to review work quality
Install tiles for pool depth | General | Low | Alroy | Pool | Materials Block | 2026-09-01 |  | 2026-09-01 | CF ordered tiles June 2026
Deck lighting to Kasa switch | General | Medium | Hank | Club House | Not started
Pool water - timer? | General | Medium | Michael | Pool | Questions | 2026-06-19 |  | 2026-06-19 | Michael, what do we need here?
Concrete wall plan with property expansion | Construction | High | Charlotte | Grounds | In planning | 2026-06-25 |  | 2026-06-25 | Need survey lines
Install second pool light | General | Low | Alroy | Pool | Materials Block | 2026-09-01 | 1 | 2026-09-02 | CF ordered second light June 2026
Fencing for dogs | Construction | Medium | Charlotte | Grounds | In planning | 2026-06-25 | 180 | 2026-12-22 | Need survey lines
Concrete driveway plan | Construction | Medium | Charlotte | Grounds | In planning |  |  | 0 | CF needs to scope project
Landscaping fencing (chainlink) | Construction | Medium | Charlotte | Grounds | In planning |  |  | 0 | How much to order
Steps and pathways to all water tanks as well as water depth measurement | General | Medium | Alroy | Grounds | Completed | 2026-06-18 | 0 | 2026-06-18 | Need to be able to easily walk to all water storage tanks. We will hopefully be getting some rain and rainwater.
Light in bar is flickering. Need to see why | General | Medium | Hank | Club House | Scheduled | 2026-06-23 |  | 2026-06-23 | When you turn on the spot lights, the light starts to flicker
Review the crack in the master lodge and ensure that it is not getting worse | General | Low | Alroy | Jasmine | Questions | 2026-06-18 |  | 2026-06-18 | The crack is in the bathroom and you can see if pretty clearly.
Fix family lodge pipe cracked club house | General | Medium | Alroy | Club House | Questions | 2026-06-18 |  | 2026-06-18 | Jerome identified
Covers for AC Units
Splitter hose
Service AC in family & master villas
AC Covers | General | Medium | Charlotte | Multiple Loc | Questions | 2026-06-18 | 3 | 2026-06-21 | Asked alecia
Service Fridge Filter | General | High | Alroy | Club House | Scheduled | 2026-06-22 | 5 | 2026-06-27 | Technican called
Appliance (fridge filter)
Review grout work in pool | General | Low | Alroy | Pool | Questions | 2026-06-18 |  | 2026-06-18 | Grout work quality
Media Room Rug | General | Low | Charlotte | Club House | In progress | 2026-06-22 | 1 | 2026-06-23 | Trim runner
Water tank cleaning | General | Medium | Alroy | Multiple Loc | Questions | 2026-06-22 | 1 | 2026-06-23 | Add chemical or scrub
Hang kitchen smoke detectors | General | Critical | Alroy | Club House | Scheduled | 2026-06-22 | 1 | 2026-06-23
Fix front door lock | General | High | Alroy | Club House | Scheduled | 2026-06-22 | 1 | 2026-06-23
Ant baits kitchen
Set up lights above dining kasa time
Formulas:
Est Completion Date = [Scheduled Start]+[Work Days]

## Grounds Projects
Task | Type | Priority | Owner | Location | Status | Start date | Est Days | Est compl | Notes
Remove mounds by trees | General | High | Jerome | Grounds | In progress | 2026-06-18 | 3 | 2026-06-21 | Team working on all beds as of 6/18
Switch club house dimmer (upside down) | General | Medium | Hank | Club House | Not started |  |  |  | Club House
Gym Gutter Review, leaking on the side so not draining into the gutter | General | High | Alroy | Gym |  |  |  |  | If you look at the corner it has water dripping and standing water meaning that the water is not getting to the tank.
Replace all black switches | General | Medium | Hank | Multiple Loc | In progress |  |  |  | Check Whole Property
Create moats for beds widen all to atleast 4 feet | General | High | Jerome | Grounds | In progress | 2026-06-18 | 8 | 2026-06-26 | Team working on all beds as of 6/18
Remove outdoor electrical switch |  | Low | Hank | Phillips | Completed | 2026-01-23 |  |  | By the pump there is old switch to remove ask Alroy
Delayed Lighting on Fan |  | Low | Hank | Multiple Loc | Completed | 2026-01-12 |  |  | Delayed start when turning on lights
Complete wall behind family lodge | Construction | Medium | Glenroy | Grounds | Questions |  |  | 0 | Bring wall around
Hang two fans | General | Low | Hank | Multiple Loc | Completed | 2026-01-12 |  |  | Media room and Master
Mr. Blacks beds - Extend 4ft & group plants | General | High | Jerome | Grounds | In progress | 2026-06-18 | 2 | 2026-06-20
Extend beds to 4 ft by ALL villas | General | Medium | Jerome | Grounds | In progress | 2026-06-18 | 8 | 2026-06-26
Plant palm & zoz grass by cedar trees | General | Medium | Alroy | Grounds | In progress |  | 4 | 1900-01-03 | When beds are complete
Service Stoves | General | Medium | Charlotte | Club House | Completed | 2026-01-13 |  |  | Reached out to chef
Pool filter | General | Critical | Michael | Grounds | Completed | 2026-01-26 |  |  | Wating for quote
All remotes hung for fams | General | Medium | Alroy | Club House | Completed | 2026-01-19
Ghost Lighting |  | High | Hank | Hibiscus | Completed | 2026-01-12 |  |  | Did Cam replace the light?
Pool steps stonework | General | Medium | Alroy | Grounds | Completed | 2026-01-16 |  |  | Prepping for Alroy
Hang Cameras | General | Critical | TomTom | Grounds | Completed | 2026-01-05 |  |  | Check all working and set up
Tub leak | General | Medium | Alroy | Jasmine | Completed | 2026-01-26 |  |  | Plumbing leaking in tub
Vinlec Pole Repair | General | Critical | Charlotte | Grounds | Completed | 2026-01-05 |  |  | Malcomb sending team out 1/6 to review
Cut grasses and plants on pool hill | General | Medium | Alroy | Grounds | Not started |  |  | 0
Hang spotlights | General | Medium | Alroy | Grounds | Completed | 2026-01-09
Slider door sticks | General | Medium | Alroy | Apple | Completed | 2026-01-14 |  |  | Door keeps coming off the track
Install Doggie Door on Villa | General | Medium | Alroy | Hibiscus | Completed | 2026-01-13
Hang key pad front door | General | Medium | Alroy | Club House | Completed | 2026-01-14
Gym Decking | General | High | Alroy | Grounds | Completed | 2026-01-05 |  |  | Est start 1/5, finish 2 weekes
Repaint step by gym | General | Low | Alroy | Grounds | Completed | 2026-01-14
Ice Maker Repair | General | High | Michael | Club House | Completed | 2026-01-12
Bar solution - paint and OSV | General | Critical | Charlotte | Club House | Completed | 2026-01-26
Order Tile Sealant | General | Critical | Charlotte | Multiple Loc | Completed | 2026-01-14 |  |  | Ordered will pick up in FLA
Fix paint cracks | General | Low | Alroy | Jasmine | Completed
Grout fix pool steps & sealant | General | High | Alroy | Grounds | Completed | 2026-01-26
Family lodge leak in ceiling | General | High | Alroy | Frangipani | Completed | 2026-01-12 |  |  | Just needs paint
Air in Plumbing Line Bar | General | Medium | Alroy | Club House | Completed | 2026-01-14
OSV AC Servicing 6 Month | General | Medium | Charlotte | Multiple Loc | Completed | 2026-01-14 |  |  | CF Called OSV 1/12
Handles/doors on french patio villas | General | Low | Charlotte | Multiple Loc | Completed |  |  |  | Jasmine and Hisbiscus
Counter brackets | General | Medium | Alroy | Club House | Completed | 2026-01-14 |  |  | CF Called OSV 1/12
Shower Glass Leaks | General | High | Alroy | Multiple Loc | Completed | 2026-01-14 |  |  | Jasmine & Orchid
Install accumulator tank in main lodge | General | Critical | Alroy | Club House | Completed
Rehang, paint bar photos | General | Medium | Alroy | Club House | Completed
Service all gym equipment | General | Critical | Alroy | Grounds | Completed
De-rust game equipment | General | Critical | Alroy | Grounds | Completed
Set up lattice by garbage | General | Critical | Alroy | Grounds | Completed | 2026-02-01
Ice maker repair | General | Critical | Alroy | Club House | Completed
Move all scones facing down |  | Low | Hank | Multiple Loc | Completed | 2026-01-12
Replace villa door handles | General | Low | Alroy | Jasmine | Completed
Replace villa door handles | General | Low | Alroy | Hibiscus | Completed
Roof fascia on villa | General | Medium | Alroy | Hibiscus | Completed
Clear grounds pumps | General | High | TomTom | Grounds | Completed
Replace villa door handles | General | Low | Alroy | Club House | Completed
Master Toilet Leaking | General | High | Alroy | Jasmine | Completed
Shelving gym | General | Low | Alroy | Grounds | Completed
Gym windows and doors | General | Medium | Alroy | Grounds | Completed
Fan in media room making buzzing noise | General | Medium | Hank | Club House | Completed
Pull all ground electical | General | High | Hank | Grounds | Not started
Furniture covers outdoor | General | Critical | Charlotte | Multiple Loc | Completed |  |  |  | Determine what is needed
Finish furniture shuffle | General | Low | Charlotte | Multiple Loc | Completed
New light above family lodge not working | General | High | Hank | Orchid | In progress
Terrace & wall in front of hibiscus lodge | Construction | High | Glenroy | Grounds | Questions |  |  | 0
Raised beds and garden | Construction | Medium | Michelle | Grounds | Not started |  |  | 0 | To start after construction complete on driveway
Ac fix 110 to 220 in club house | General | Medium | Hank | Club House | Completed
Driveway and landscaping plan | Construction | Medium | Charlotte | Grounds | In progress |  |  | 0
Source metal fountains | General | Low | Michelle | Grounds | Materials Block |  |  | 0
Coconut Husk for beds | General | Critical | Alroy | Grounds | In progress | 2026-06-18 |  | 2026-06-18 | Text Michelle 6/18 to order
Order fertilizer (white) | General | Medium | Charlotte | Grounds | In progress | 2026-06-18 |  | 2026-06-18 | Orderd from Michelle
Club switch timers | General | Low | Hank | Club House | In progress |  |  |  | Verify with Hank
Pathway to the sauna | General | Low | Glenroy | Grounds | Not started |  |  | 0
Replant the palms and trees around sauna area | General | Medium | Jerome | Grounds | Not started |  |  | 0
Pool step slip issue | General | Critical | Alroy | Grounds | Completed | 2026-01-29 |  |  | Calling bunion
Order splitter water tanks | General | High | Alroy | Grounds | Not started |  |  | 0
Add cleaner to water tanks | General | Low | Jerome | Grounds | Not started | 2026-06-22 | 4 | 2026-06-26 | CF to figure out ratios
0
0
0
0
Villa switch timers | General | Low | Charlotte | Club House | Completed |  |  |  | CF needs to test
Solar light install & review | General | Medium | Alroy | Grounds | Completed
0
0
Cold plungs hook up | General | High | Hank | Grounds | Completed |  |  |  | Sat. installation
0
0
Pool light (second one needs replacement) | General | Low | Hank | Grounds | In progress |  |  |  | waiting on hank
Timer for entrance pond | General | Low | Hank | Grounds | In progress |  |  |  | waiting on hank
0
0
Villa sinks draining slowly | General | Medium | Alroy | Multiple Loc | Completed |  |  |  | CF brought drains and tools 04/28
0
0
0
0
0
Remove all debris yard | General | High | Alroy | Grounds | Completed
Order concrete & block maker | General | Low | Charlotte | Multiple Loc | Completed | 2026-04-30
Media Room Simply Lock | General | Medium | Charlotte | Club House | Completed |  |  |  | Wrong lock, new one on way
Fridge & freezer service | General | High | Alroy | Club House | Completed | 2026-01-29 |  |  | Fridge and freezer technician
Deck lighting to Kasa switch | General | Medium | Hank | Club House | Not started
Ant baits kitchen
Set up lights above dining kasa time
Formulas:
Est compl = [Start date]+[Est Days]

## Grounds_Weekly Checklist
Grounds Weekly Checklist | Jermone | _______________ | A Sign Off | _______________
Date | Start Date | _______________ | End Date | _______________
| M | T | W | Th | F
All Clocked In | FALSE | FALSE | FALSE | FALSE | FALSE
Assign Garden Tasks | FALSE | FALSE | FALSE | FALSE | FALSE
Lunch Break Logged | FALSE | FALSE | FALSE | FALSE | FALSE | Salt water system
TOOLS AWAY | FALSE | FALSE | FALSE | FALSE | FALSE | Mulch / compost
Generator Room Clean | FALSE | FALSE | FALSE | FALSE | FALSE | No plastic bags (especially for garden stuff)
Gasoline (Number of Cans) | #_____ | #_____ | #_____ | #_____ | #_____ | No raking bare ground.
Kitchen Garbage Out | FALSE | FALSE | FALSE | FALSE | FALSE | More effiency
Garbage Area Clean | FALSE | FALSE | FALSE | FALSE | FALSE
Plants Watered | FALSE | FALSE | FALSE | FALSE | FALSE
Seating Area Tidy | FALSE | FALSE | FALSE | FALSE | FALSE
Yard Construction Cleaned Up | FALSE | FALSE | FALSE | FALSE | FALSE
Morning List | M | T | W | Th | F
Cushions & Towels (Guests) | FALSE | FALSE | FALSE | FALSE | FALSE
Clean Pool & Sweep Deck | FALSE | FALSE | FALSE | FALSE | FALSE
Open & Sweep Gym | FALSE | FALSE | FALSE | FALSE | FALSE
Club House Deck & Table | FALSE | FALSE | FALSE | FALSE | FALSE
Covers On (No Guests) | FALSE | FALSE | FALSE | FALSE | FALSE
Water Catchment (Weekly) | 1x Weekly | Level Check
Club Villa Gutter | FALSE | ______ %
Jasmine Gutter | FALSE | ______ %
Hisbiscus Gutter | FALSE | ______ %
Buttercup Gutter | FALSE | ______ %
Bougainvillea Gutter | FALSE | ______ %
Plum Rose Gutter | FALSE | ______ %
Sidewalk Drains | FALSE | ______ %
Club House Tanks | FALSE | ______ %
Jasmine Tanks | FALSE | ______ %
Hisbiscus Tanks | FALSE | ______ %
Buttercup Tanks | FALSE | ______ %
Bougainvillea Tanks | FALSE | ______ %
Sidewalk Drains | FALSE | ______ %
Pool | M | T | W | Th | F
Clean Filter & Pool Daily | FALSE | FALSE | FALSE | FALSE | FALSE
Salt and Pump Check | FALSE | FALSE | FALSE | FALSE | FALSE
Lighting (2 x Monthy) | 1 | 2
Clean All Villa Lights | FALSE | FALSE
Wipe Pathway Lights | FALSE | FALSE
Wipe Solar Panels Cameras | FALSE | FALSE
Other (2 x Monthly) | 1 | 2
Pressure Wash | FALSE | FALSE
Gym & Game Equip (De-Rust) | FALSE | FALSE
Gym Windows Clean | FALSE | FALSE
Wash Out Garbage Cans | FALSE | FALSE
Clean Cold Plunge | FALSE | FALSE
Termite Treatment | FALSE | FALSE
Projects
Mulch (coconut husk all beds) | FALSE
Set up Compost | FALSE

## Prevention_Checklist
Maintenance Prevention Checks Date:
Weekly Prevention |  | Notes
Add Maintenance Issues to Log | FALSE
Plum Rose Water Tanks Full | FALSE
Laundry & Dish Machines Functional | FALSE
All Security Cameras Online | FALSE
All Camera Batteries Full | FALSE
All Lock Batteries Full | FALSE
Generator Operational w/ diesel | FALSE
Monthly Building Checks | Club | Jasmine | Hibiscus | Buttercup | Orchid | Apple | Frang
Lighting & Ceiling Fans Operational | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Plumbing - Leak Free | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Fridge, Freezer, Ice Working | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Doors & Windows On Track | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Water Pumps Functional | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Hot Water Heater Operational | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
A/C Checks | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Termite Damage & Repairs | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Solar Panels Clean | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Flooring/Tile Inspection | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Clean Water Tanks | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Water Tank Level (% Full) | _____% | _____% | _____% | _____% | _____% | _____% | _____%
Patio Covers on All Furniture | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Pest Control | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Club House Doors Maintenance | FALSE